## Estimate
Priority | Feature Description | Efforts (Days) 1. Pls consider all aspects e.g. development, testing, deployment, ECN times, regulatory, documentation changes etc. 2. Consider all firmware, PCSW, App e.g. bootloaders, Main, Aux, Annunciator, PCSW, Programmer Utility, Android App, iOS APP, GW as applicable | [6 empty] | Dependencies | Queries | Inputs from PdM What areas are targeted ? (Revenue/good to have/ user experience etc.) | Remarks | HW | Mech | FW | GW | PCSW | Mobile App | PgM | PdM/Tech Support | MFRng | Tech Pub
|  | HW | FW | GW | PCSW | Mobile App | MECH | SQA
1 | Pigtail cables for POTS and IP Gateway connections as short-term fix for Gateway access | [9 empty] | User experience, ease-of-use, reduce install time | [MJ]: If Cost is acceptable, there should be no impediment to implement. | R/A | R/A | I | I | I | I | I | S/C | S/I
2 | New PIDs for addressable panels with Gateway installed at the factory | [9 empty] | User experience, ease-of-use, reduce install time |  | S | R/A | I | I | I | I | I | I | S/I
3 | TMC analysis and reduction | [9 empty] | Revenue and margin, improve competitive position |  | R/A | R/A | I | I | I | I | S | S/I | A/I/C
4 | Ability to disable secondary POTS/IP/Cell so false faults are not sent. You currently cannot disable the secondary. If you do not have two separate connections, you will get a fault on the unconnected channel. |  | 20 | 15 | [6 empty] | AHJ will not accept system showing troubles. |  | I | I | R/A | R/A | R/A | R/A | I | I/C
4b | New Entry - ICT/FCT time reduction for Tier 3 family | [6 empty] | Need to test panel after running FCT |  | 1. Time spent in FCT by factory. We have ICT numbers but those files do not mention FCT | Margin, improve factory throughput | New Entry | S | S | R/A | R/A | I | I | S | I | I
5 | SafeLINC for Foundation, new addressable panel firmware version. |  | 15 | 35 | [5 empty] | 1. [MJ]: Could it be introduced to SAFELINC project ? | Recurring revenue, differentiating feature | [MJ]: Could it be introduced to SAFELINC project ? | S | R/A | I | I | I | I | I | I | S/I
6 | Addressable enclosure redesign to relocate Gateway to a more accessible location and Power supply cover. - Position change, Validation, Pre-compliance, release, UL validation (in #6) | [9 empty] | User experience, ease-of-use, reduce install time |  | R/A | R/A | A | A | I | I | I | I | I
7 | 4G modem for internal Gateway. Works with external cabinet now. - Setup, Validation, Pre-compliance, UL approval (10 weeks), FCC, Include #6 as well |  |  | 5 | [6 empty] | Recurring revenue, differentiating feature | [MJ]: We can look forward to have less invasive methods to use 4G modems. If possibility of using any third part modem, can be explored in long run. | R/A | S | S | S | I | I | I | I | S/I
8 | USB Ground Fault on addressable panels when PC is pulled into AC power. - Feasibility/solution POC, Validation, Design change (Schematic, Layout, FAB, pre-compliance, UL Validation), submit with change #7 | [9 empty] | User experience |  | R/A | R/A | R/A | R/A | R/A | I | S/I | I/C | S/I/C
9 | Retrofits – The current Foundation product line is aimed at new installations. Are there any new options / accessories that could be introduced to make it easier for a Foundation panel to replace an existing low-end competitor system like Fire-Lite, Silent Knight – i.e. trim rings to fit over competitor installed box openings, blocks that make it easier to use existing wiring, etc.? | [8 empty] | 1. [MJ]: We need more details on the competitor setup and Scope. Along with it, would be helpful to have any installation diagrams and setup pictures being targeted here. | Revenue, ease-of-use, reduce install time | [MJ]: We need more details on the competitor setup and Scope. Along with it, would be helpful to have any installation diagrams and setup pictures being targeted here. | S | S | R/A | R/A | R/A | R/A | I | I/C
10 | Service – Not sure if any software/firmware mod could be included to remind owners that service is due on this low-end, stand-alone system? After x years without a “service number” being entered a trouble flashes, etc.? (Mobile App, SAFELINC Etc.) - | [8 empty] | [MJ]: We need to know: 1. Who does this service for JCI ? 2. What is covered under service ? 3. Who maintains the record with checklist ? 4. does it have considerable revenue for such low end panels ? can be tracked from SAFELINC Is impactful. 5. Which Parameter to say that service is required ? (R&D + PdM Sales) 6. What about Annunciator servicing. is this for whole Family ? 7. What is service number? is it serial number | Revenue | [MJ]: We need to know: 1. Who does this service for JCI ? 2. What is covered under service ? 3. Who maintains the record with checklist ? 4. does it have considerable revenue for such low end panels ? can be tracked from SAFELINC Is impactful. 5. Which Parameter to say that service is required ? (R&D + PdM Sales) 6. What about Annunciator servicing. is this for whole Family ? 7. What is service number? is it serial number | S | S | R/A | R/A | R/A | R/A | S | S/C | S/I
11 | Wholesale distribution sales (highly confidential – do not share with anyone. Need a new brand/industrial design/part number scheme/packaging for selling wholesale. - | [8 empty] | Need clarifications from PDM | Revenue, expanded market share | [MJ]: Impact areas Brand labels, regulatory, could be FW due to brand information. | R/A | R/A | R/A | R/A | R/A | R/A | S | S/I/C | S/I/C
12 | Releasing version of Foundation conventional panel for Ansul and Simplex/Autocall to possibly replace the Z10/4004R - | [8 empty] | 1. We need MRD for this activity in order to estimate. 2. We will also need physical samples at Pune 3. Should not be considered in NA continuation, separate project needed for it | Revenue – replace Honeywell product with JCI product | [MJ]: We would need details of Z10/4004R (Marketing datasheet, manuals, HDS etc.) and Physical samples at Pune. | R/A | R/A | R/A | R/A | R/A | R/A | S | S/I | S/A
13 | New Entry: Tier 3 Operational manual Translation changes | [8 empty] | Need clarifications from PDM | Ease-of-use |  | R/A | I | R/A | R/A | R/A | R/A | I | I |  | S
14 | New Entry: front panel display and the annunciator display should match at all times and display System Normal when in a quiescent state | [8 empty] | 1. We
15
BELOW ARE INTERNALLY PLANNED TASKS. NOT TO BE SHARED WITH PGM, PDM WITHOUT INTERNAL APPROVALS. PLEASE ADD ROWS AS NEEDED
14 | Defect Fixes: Pls add list e.g. Loop counter in JSON parser (Multiple defects, integration testing) |  | 20 | 10
15 | Optimizations or Performance Improvement (No JSON optimization needed) e.g. GW startup time reduction, Panel UI for GW Progress |  | 10 | 10
16 | From tech support call: Pete uploaded a screenshot showing the Simplex PC programmer time setup. It clearly shows time/date formats not supported by the panel (DD/MM/YY). Can you please correct this in the next PC programmer revision? | [11 empty] | R/A: R/A
17 | From tech support call: Request of addition of power supply cover add Panel . Something similar to the power supply cover used on the 2004/2008 Foundation panels
18 | From tech support call: Software Compatibility chart in SRD 2. Panel programmer to update with Latest FW
19 | QR code scan feature from Foudation Series Console to add devices based on device QR code.
20 | New Entry: Conventional Annunciator and panel FCT cleanup. Need to restore data in sectors being tested
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61

## Bug list in Jira as on 20-Jan
Issue key | Summary | Component/s | Component/s2 | Component/s3 | Status | Reporter | Custom field (Originator Group) | Labels | Labels4 | Labels5 | Labels6 | Created | Comment FW
FDNAT3ADDR-789 | Gateway didn't configure in first attempt when Configuration set from mobile app and transferred via NFC | MobileApp |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2023-01-17 12:11
FDNAT3ADDR-788 | Console is not showing address book name when path set to PSTN | MobileApp | PCSW |  | To Do | jkulkapv | SQA |  |  |  |  | 2023-01-17 11:27
FDNAT3ADDR-787 | Simplex DAPS module is not getting enrolled in the panel database.Â | Main Panel Code |  |  | To Do | jdatiru | SQA |  |  |  |  | 2023-01-16 17:51
FDNAT3ADDR-786 | NAC Trigger options are not getting displayed on same screen until scrolled up on iOS 16.2 for Autocall brand | MobileApp |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2023-01-13 15:34
FDNAT3ADDR-785 | When entering text/characters in site or panel notes to the its limit, the mobile app crashes | MobileApp |  |  | To Do | jdatiru | SQA | Continuation |  |  |  | 2023-01-13 15:29
FDNAT3ADDR-784 | Issue for assigned zones and Zone Labels | MobileApp |  |  | To Do | jmarkam | SQA |  |  |  |  | 2023-01-11 17:26
FDNAT3ADDR-783 | Mobile app screen should remain at the same location after editing/saving configuration for a device on the list of devices page. | MobileApp |  |  | To Do | jdatiru | SQA | Continuation |  |  |  | 2023-01-11 16:02
FDNAT3ADDR-782 | Mobile app doesn't display default trigger Option- NA for Sounder and Remote LED in Spanish language | MobileApp |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2023-01-11 15:48
FDNAT3ADDR-781 | Application is getting crashed when clicked on panel display page from mobile app | MobileApp |  |  | To Do | jdatiru | SQA |  |  |  |  | 2023-01-11 15:40
FDNAT3ADDR-780 | Mobile app exported JSON file shows wrong details related to device gateway mapping when imported into the console. | MobileApp | PCSW |  | To Do | jdatiru | SQA | Continuation |  |  |  | 2023-01-11 15:27
FDNAT3ADDR-779 | Mobile app exported JSON file shows wrong details for when imported in console | MobileApp | PCSW |  | To Do | jkulkapv | SQA | Continuation |  |  |  | 2023-01-10 15:14
FDNAT3ADDR-778 | Panel gives CRC error after NFC transfer, if special characters are used in Panel Notes from Mobile APP. | MobileApp |  |  | To Do | jdatiru | SQA | Mobile |  |  |  | 2023-01-06 15:59
FDNAT3ADDR-777 | When user update base option from sounder to standard , trigger option screen is not getting updated | MobileApp |  |  | To Do | jkulkasi | SQA |  |  |  |  | 2023-01-06 12:43
FDNAT3ADDR-776 | FS T3 Mobile app is displaying a "Not supported QR code" error for few supported modules of both brands.Â | Hardware | PO |  | To Do | jdatiru | SQA |  |  |  |  | 2023-01-05 11:22
FDNAT3ADDR-775 | Remote LED is not getting activated when set to Point trigger from mobile APP. | Main Panel Code | MobileApp |  | To Do | jkulkapv | SQA |  |  |  |  | 2023-01-04 11:11
FDNAT3ADDR-774 | PSTN line validation not working as expected when configured from mobile app | MobileApp |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2023-01-03 18:16
FDNAT3ADDR-773 | Exported File should be allowed to save in mobile with Blank spaces and other extensions |  |  |  | To Do | jgahers | SQA |  |  |  |  | 2023-01-03 15:23
FDNAT3ADDR-772 | 0.0.39 UAT build - Mobile App Screen suddenly shown Blank screen while using App | MobileApp |  |  | To Do | jgahers | SQA | Monitor |  |  |  | 2023-01-03 15:05
FDNAT3ADDR-771 | UAT 0.3.39 Mobile App Usability Related Observation | MobileApp |  |  | To Do | jgahers | SQA | Testing |  |  |  | 2023-01-03 12:18
FDNAT3ADDR-770 | For Zone, NAC Labels & Central Station Gateway Account Code should not allow Blank spaces, as currently all Blank spaces are allowed as labels name | MobileApp |  |  | To Do | jgahers | SQA |  |  |  |  | 2023-01-03 12:16
FDNAT3ADDR-769 | Gateway account code accepts special characters and letters in mobile app, post that gateway configure trouble is generated continuously & events are not received on server | MobileApp |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2023-01-02 12:38
FDNAT3ADDR-768 | Panel displays incorrect screen saver when special characters and letters set from mobile app | MobileApp |  |  | To Do | jkulkasi | SQA |  |  |  |  | 2023-01-02 12:10
FDNAT3ADDR-767 | While importing file in mobile app ,if user pressed back key at file location page, mobile app gives error and goes to Panels page in iOS; whereas in android it stays in import file page | MobileApp |  |  | To Do | jkulkasi | SQA |  |  |  |  | 2022-12-29 18:18
FDNAT3ADDR-766 | Cancel button is not available for Android while transferring File via NFC, whereas it is available in iOS | MobileApp |  |  | To Do | jkulkasi | SQA |  |  |  |  | 2022-12-29 18:10
FDNAT3ADDR-765 | NAC is not getting activated when set to default-Panel trigger from mobile app | Main Panel Code | MobileApp |  | To Do | jkulkapv | SQA |  |  |  |  | 2022-12-29 15:28
FDNAT3ADDR-764 | Sounder is not getting activated when set to Point trigger from mobile APP. | Main Panel Code | MobileApp |  | To Do | jkulkapv | SQA |  |  |  |  | 2022-12-29 15:00
FDNAT3ADDR-763 | Complete text not displayed for Base options in mobile app | MobileApp |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2022-12-28 19:16
FDNAT3ADDR-762 | Mobile app gets closed, when NFC transmission is stopped due to phone screen lock, & transmission does not starts when app is reopened | MobileApp |  |  | To Do | jkulkasi | SQA |  |  |  |  | 2022-12-28 18:23
FDNAT3ADDR-761 | Autocall app icon showing in blue color for ios 15 ver & red for ios 16.1.1 | MobileApp |  |  | To Do | jkulkasi | SQA |  |  |  |  | 2022-12-27 11:37
FDNAT3ADDR-760 | The mobile app gives an "export error" popup while sending the configuration via email. | MobileApp |  |  | To Do | jdatiru | SQA |  |  |  |  | 2022-12-27 11:12
FDNAT3ADDR-759 | Mobile app doesn't ask for camera permission while scanning QR code if user has denied permission first time | MobileApp |  |  | To Do | jkulkasi | SQA |  |  |  |  | 2022-12-27 11:08
FDNAT3ADDR-758 | Alarm condition is not getting reset for ZAM module. | Hardware |  |  | Analysis | jdatiru | SQA |  |  |  |  | 2022-12-12 14:40
FDNAT3ADDR-753 | Console is showing bad checksum error while importing panel programming file in console | PCSW |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2022-09-22 19:26
FDNAT3ADDR-752 | Help file loading status displayed 100% initially on UI, even though process is still in progress | Main Panel Code |  |  | To Do | jdatiru | SQA |  |  |  |  | 2022-09-22 18:00
FDNAT3ADDR-751 | Internal defect ¦ Second power on onwards in factory mode, Zone assignment screen appears intermittently | Main Panel Code |  |  | To Do | jbiradc | R&D Firmware |  |  |  |  | 2022-09-21 11:18
FDNAT3ADDR-747 | "NO Answer" trouble occurs and restores automatically for the Autocall smoke sensor. | Main Panel Code |  |  | To Do | jdatiru | SQA | Autocall | Device_Specific |  |  | 2022-08-18 17:55
FDNAT3ADDR-746 | Load programming is not working as expected using USB stick | Main Panel Code |  |  | To Do | jsatreg | SQA |  |  |  |  | 2022-08-12 17:16
FDNAT3ADDR-745 | Negative scenario - System is not aborted when walk test is activated for detector only | Main Panel Code |  |  | To Do | jsatreg | SQA |  |  |  |  | 2022-08-11 12:53
FDNAT3ADDR-744 | Detector is not detecting alarm condition when we configured all zone pull station only for walktest | Main Panel Code |  |  | To Do | jsatreg | SQA |  |  |  |  | 2022-08-11 12:46
FDNAT3ADDR-743 | The panel is not detecting primary and secondary path trouble after the firmware update.Â | Gateway | Main Panel Code |  | To Do | jdatiru | SQA | gateway |  |  |  | 2022-08-10 19:22
FDNAT3ADDR-742 | The sounder base which is configured for CO/Pri2Â is not getting silenced when the panel is in fault condition and the silence key is pressed from the annunciator. | Main Panel Code |  |  | To Do | jdatiru | SQA |  |  |  |  | 2022-08-10 14:22
FDNAT3ADDR-741 | Sounder base activated for any event though it is not enabled | Main Panel Code |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2022-08-10 11:32
FDNAT3ADDR-738 | Restore alarm event log when devices activated in Walktest | Main Panel Code |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2022-08-03 15:27
FDNAT3ADDR-737 | Inconsistent sounder behavior observed | Hardware | Main Panel Code |  | To Do | jkulkapv | SQA | Autocall | board_specific |  |  | 2022-07-29 15:38
FDNAT3ADDR-730 | "Prog data main controller" trouble observed after flashed released mot and hex file. | Main Panel Code |  |  | To Do | jdatiru | SQA | Continuation |  |  |  | 2022-07-13 00:30
FDNAT3ADDR-726 | Panel serial number not displayed in console when panel in default condition | PCSW |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2022-06-27 17:36
FDNAT3ADDR-725 | Enrolled devices are getting 255 address when created No answer trouble and restored | Main Panel Code |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2022-06-23 22:51
FDNAT3ADDR-724 | Sometimes panel got stuck into NFC page when we stop NFC file transmission before successful completion of file transfer | Main Panel Code | MobileApp |  | To Do | jsatreg | SQA |  |  |  |  | 2022-06-20 23:22
FDNAT3ADDR-723 | Database got erased when panel kept on battery supply for long duration | Main Panel Code |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2022-06-20 19:30
FDNAT3ADDR-721 | After Doing the Right Short/Left short Trouble Counter is mismatch in Firestrom | Main Panel Code |  |  | To Do | jtiwarsh | SQA |  |  |  |  | 2022-06-16 23:02
FDNAT3ADDR-720 | Portuguese language string related issue in Annunciator | Main Panel Code |  |  | To Do | jsatreg | SQA |  |  |  |  | 2022-06-16 19:37
FDNAT3ADDR-717 | Panel stuck in gateway configuring loop after adding new mapping type in configuration. | Gateway | PCSW |  | To Do | jdatiru | SQA | Gateway |  |  |  | 2022-06-15 23:21
FDNAT3ADDR-716 | Devices images displayed Incorrect in Autocall mobile app | MobileApp |  |  | In Progress | jkulkapv | SQA | Autocall | REOPEN |  |  | 2022-06-15 17:27
FDNAT3ADDR-714 | Abnormal behaviour observed on Autocall 2250 panel. | Main Panel Code |  |  | To Do | jdatiru | SQA | Autocall |  |  |  | 2022-06-10 17:05
FDNAT3ADDR-712 | Label for Disable>Dis List and View list>Dis List is displayed as 'Analyze' | Main Panel Code |  |  | To Do | jsatreg | SQA |  |  |  |  | 2022-06-06 23:31
FDNAT3ADDR-711 | Manual Updates | PO |  |  | To Do | jgandhag | R&D Firmware | Documentation |  |  |  | 2022-06-02 19:04
FDNAT3ADDR-709 | Enable/disable functionality using shortcut key is not working as expected when multiple device/modules disabled | Main Panel Code |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2022-06-01 23:18
FDNAT3ADDR-708 | TRELAY point type is not getting reflected in panel & console if set it from mobbile app | MobileApp |  |  | To Do | jkulkasi | SQA |  |  |  |  | 2022-05-26 21:33
FDNAT3ADDR-705 | FW upgrade Related Observations | Main Panel Code |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2022-05-13 20:37
FDNAT3ADDR-703 | NFC: Configuration download time in Android is much higher than iOS timings | MobileApp |  |  | To Do | jgandhag | R&D Firmware |  |  |  |  | 2022-05-04 18:24
FDNAT3ADDR-701 | Panel got stuck after RESET completed. | Main Panel Code |  |  | To Do | jdatiru | SQA |  |  |  |  | 2022-04-25 18:25
FDNAT3ADDR-698 | For iPhone 12 & iPhone 13 mini NFC tag is not getting detected with panel cover | MobileApp |  |  | To Do | jkulkasi | SQA |  |  |  |  | 2022-04-21 15:29
FDNAT3ADDR-697 | Do association functionality not work as expected in the Autocall console. | PCSW |  |  | To Do | jdatiru | SQA | Autocall |  |  |  | 2022-04-20 22:39
FDNAT3ADDR-696 | The device details page displayed the wrong information like delay to alarm/warning. | PCSW |  |  | To Do | jdatiru | SQA |  |  |  |  | 2022-04-20 21:17
FDNAT3ADDR-695 | IP module current ratings displayed in battery calculation page. | PCSW |  |  | To Do | jdatiru | SQA |  |  |  |  | 2022-04-20 20:51
FDNAT3ADDR-694 | In analyze, annunciator status displayed Ok even if OLD FW version is present | Main Panel Code |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2022-04-20 15:26
FDNAT3ADDR-693 | For QR code addressing via NFC all connected devices must be set for Address 255 | MobileApp |  |  | To Do | jkulkapv | SQA | documentation |  |  |  | 2022-04-19 23:48
FDNAT3ADDR-692 | Annunciators removed from database when configuration sent via NFC | MobileApp |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2022-04-19 23:34
FDNAT3ADDR-691 | MIM is not getting address when file transferred via NFC | PO |  |  | Analysis | jkulkapv | SQA | Autocall |  |  |  | 2022-04-19 23:25
FDNAT3ADDR-690 | NFC Tag is not detected for Google Pixel 5A ,5g phone | MobileApp |  |  | To Do | jkulkasi | SQA |  |  |  |  | 2022-04-18 17:13
FDNAT3ADDR-689 | Incorrect images displayed for the detector and pull station in the Autocall console. | PCSW |  |  | To Do | jdatiru | SQA | Autocall |  |  |  | 2022-04-14 23:39
FDNAT3ADDR-685 | Device got activated automatically after Hardware RESET | Main Panel Code |  |  | To Do | jkulkapv | SQA | Autocall | Device_Specific |  |  | 2022-04-06 19:05
FDNAT3ADDR-683 | Relay 3 Function type not displayed in Analyze Menu | Main Panel Code |  |  | To Do | jkulkapv | SQA | Need_Reproduction |  |  |  | 2022-04-05 23:35
FDNAT3ADDR-681 | Device with out-of-range address gets enrolled when connected with 255 address. | Main Panel Code |  |  | To Do | jdatiru | SQA | legacy |  |  |  | 2022-04-04 20:33
FDNAT3ADDR-680 | Loop Return Open not detected when short created on right side in class A | Main Panel Code |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2022-04-01 18:07
FDNAT3ADDR-677 | Zone disable trouble generated automatically after Firmware update using a USB stick & PC Console | Main Panel Code |  |  | To Do | jdatiru | SQA | Need_Reproduction | Simplex |  |  | 2022-03-31 16:13
FDNAT3ADDR-672 | Panel created JSON file not imported in Autocall console | PCSW |  |  | To Do | jkulkapv | SQA | Autocall |  |  |  | 2022-03-24 15:58
FDNAT3ADDR-671 | DAPS enrolling not working as expected | Main Panel Code |  |  | To Do | jkulkapv | SQA | Autocall | Device_Specific |  |  | 2022-03-24 00:18
FDNAT3ADDR-669 | RIM and ZAM module enrolling not working as expected | Main Panel Code |  |  | To Do | jkulkapv | SQA | Autocall | Device_Specific |  |  | 2022-03-24 00:04
FDNAT3ADDR-667 | NFC transmission fails if phone is placed on designated location and then transmission commenced | Main Panel Code | MobileApp |  | To Do | jdatiru | SQA | Continuation |  |  |  | 2022-03-19 16:29
FDNAT3ADDR-665 | AUTOCALL console not accepting detector : Smoke+Heat | PCSW |  |  | To Do | jkhabym | R&D Firmware | PC-SW |  |  |  | 2022-03-10 21:56
FDNAT3ADDR-664 | While testing with android we had to remove the safety cover from the panel for detection of the NFC tag. | Main Panel Code | Mechanical | MobileApp | To Do | jdatiru | SQA | Continuation |  |  |  | 2022-03-09 01:23
FDNAT3ADDR-663 | Sometimes new tag is detected by the Android App with manufacturer details. | MobileApp |  |  | To Do | jdatiru | SQA | Continuation |  |  |  | 2022-03-09 01:12
FDNAT3ADDR-662 | Abnormal behaviour after default data. | Main Panel Code |  |  | To Do | jdatiru | SQA |  |  |  |  | 2022-03-09 00:33
FDNAT3ADDR-661 | Panel Serial number changed intermediately. | Main Panel Code |  |  | Analysis | jdatiru | SQA | Continuation |  |  |  | 2022-03-09 00:28
FDNAT3ADDR-660 | Mobile app is not able to scan QR code of particular detector. | MobileApp | PO |  | To Do | jdatiru | SQA | Continuation |  |  |  | 2022-03-03 00:59
FDNAT3ADDR-657 | "NFC tag not detected" error not displayed on iOS. | MobileApp |  |  | In Progress | jdatiru | SQA | Continuation |  |  |  | 2022-02-28 20:41
FDNAT3ADDR-653 | Panel 2050 is showing INVALID under Program when device address change from hard to soft | Main Panel Code |  |  | Analysis | jshar5 | Product Support | Continuation |  |  |  | 2022-02-28 19:27
FDNAT3ADDR-652 | Device QR Code scanning issue | MobileApp | PO |  | To Do | jshar5 | Product Support | Continuation |  |  |  | 2022-02-28 19:20
FDNAT3ADDR-639 | Panel SUSPEND Trouble is not handled for CSG | Gateway |  |  | Analysis | jtisum3 | R&D Firmware | Continuation | NA-Foundationseries2050and2250 |  |  | 2022-01-29 17:06
FDNAT3ADDR-635 | Devices/modules images are incorrect | PCSW |  |  | To Do | jkulkapv | SQA | Continuation |  |  |  | 2022-01-20 16:54
FDNAT3ADDR-632 | Relay/NAC warnings not displayed in verify setup when not connected to any input device | PCSW |  |  | To Do | jkulkapv | SQA | Continuation |  |  |  | 2022-01-17 18:41
FDNAT3ADDR-631 | Installation manual is not available in Console | PCSW |  |  | To Do | jkulkapv | SQA | Continuation |  |  |  | 2022-01-17 17:06
FDNAT3ADDR-629 | Incorrect information displayed in the panel when Cellular is set as a communication channel in mobile APP and transferred | Main Panel Code |  |  | To Do | jdatiru | SQA | Continuation |  |  |  | 2022-01-14 15:36
FDNAT3ADDR-627 | Panel does not detect WRONG BRAND when Autocall RIAM is connected | Main Panel Code |  |  | To Do | jsubral | SQA | Continuation | PdM_Agreement |  |  | 2022-01-13 18:16
FDNAT3ADDR-620 | After autoaddressing, some devices are not getting addressed | Main Panel Code |  |  | To Do | jsatreg | SQA | Continuation |  |  |  | 2022-01-07 15:41
FDNAT3ADDR-616 | After device mapping, MIM and Pull station is showing "INVALID" Device type | Main Panel Code |  |  | Analysis | jsatreg | SQA | Autocall | Continuation | PdM_Agreement | Simplex | 2022-01-05 19:51
FDNAT3ADDR-611 | When Relay module is configured for ACTIVE ON DISABLEMENT and sent to panel, Panel displays point type as NOTUSE | MobileApp |  |  | To Do | jsubral | SQA | Continuation |  |  |  | 2022-01-04 18:10
FDNAT3ADDR-610 | Mobile App is not able to read the QR code present in SNM, SAPS and Mini IAM module. | MobileApp | PO |  | To Do | jsubral | SQA | Autocall | Continuation |  |  | 2022-01-04 17:57
FDNAT3ADDR-608 | Gateway disabled status showing extra characters in Analyze Manu. If communication channel configured for primary IP. | Main Panel Code |  |  | To Do | jdatiru | SQA | Continuation |  |  |  | 2022-01-03 19:45
FDNAT3ADDR-605 | Sometime event details page is not displayed on the panel after pressing ACK key | Main Panel Code |  |  | To Do | jsatreg | SQA | Continuation |  |  |  | 2022-01-03 17:33
FDNAT3ADDR-602 | In Analyze menu Up key is not working to check other parameter values for SNM | Main Panel Code |  |  | Blocked | jsatreg | SQA | Continuation |  |  |  | 2021-12-30 15:17
FDNAT3ADDR-601 | False double address error message is displayed on the panel during auto enrolling | Main Panel Code |  |  | Blocked | jsatreg | SQA | Monitor |  |  |  | 2021-12-30 15:03
FDNAT3ADDR-599 | Console taking too much time to send configuration to panel | Main Panel Code | PCSW |  | In Progress | jsatreg | SQA | Continuation | Monitor |  |  | 2021-12-28 15:48
FDNAT3ADDR-597 | "Non-resettable" functionality is not working as expected while sending configuration from PCSW | Aux Processor_575 |  |  | In Review | jsatreg | SQA | Continuation | PdM_Agreement |  |  | 2021-12-27 18:01
FDNAT3ADDR-594 | Multiple Zone disabled trouble generated on Panel automatically after Power ON when Panel kept OFF overnight | Main Panel Code |  |  | To Do | jkulkapv | SQA | Continuation |  |  |  | 2021-12-23 17:57
FDNAT3ADDR-591 | "Response from panel timed out" error message is displayed on the PCSW while sending the configuration to the panel | Main Panel Code |  |  | To Do | jsatreg | SQA | PdM_Agreement |  |  |  | 2021-12-22 12:03
FDNAT3ADDR-590 | Locate loop brake functionality is not working as expected with 1 Km cable |  |  |  | Analysis | jsatreg | SQA | Continuation | PdM_Agreement |  |  | 2021-12-22 11:41
FDNAT3ADDR-581 | City circuit trouble is getting restored automatically when alarm condition is generated on panel (Create City ckt trouble using switch or Remove EOLR) | Main Panel Code |  |  | To Do | jsatreg | SQA | Not_Critical |  |  |  | 2021-12-15 14:38
FDNAT3ADDR-572 | Detector sensor LED didnâ€™t turn OFF after reset. | Main Panel Code |  |  | To Do | jdatiru | SQA | Continuation | SSD_Detector_Specific |  |  | 2021-12-08 18:21
FDNAT3ADDR-571 | While programming if ESC key pressed panel displays No activity page | Main Panel Code |  |  | To Do | jkulkapv | SQA | Not_Critical |  |  |  | 2021-12-08 17:51
FDNAT3ADDR-569 | When the sounder base of the triple sensor device is activated, the detector LED glows in orange color. | Main Panel Code |  |  | Analysis | jdatiru | SQA | SSD_Detector_Specific |  |  |  | 2021-12-06 12:03
FDNAT3ADDR-559 | SSD devices observations. | Main Panel Code | PO |  | To Do | jdatiru | SQA | Continuation | SSD_Detector_Specific |  |  | 2021-11-29 15:34
FDNAT3ADDR-541 | False alarm generated for Triple sensor when Out of range trouble was present and performed enrolling | Main Panel Code |  |  | Blocked | jkulkapv | SQA | Continuation | PdM_Agreement |  |  | 2021-11-12 14:39
FDNAT3ADDR-539 | When USB-USB cable is connected for printer the panel door isn't closing | Mechanical |  |  | To Do | jsubral | R&D Firmware | Mechanical_to_Close |  |  |  | 2021-11-12 02:40
FDNAT3ADDR-526 | Internal Issue 01.01.01: Wrong panel type message box is coming two times | PCSW |  |  | To Do | jgosavj | R&D PC Software | Continuation |  |  |  | 2021-11-01 15:23
FDNAT3ADDR-521 | When Exported JSON file from console to the mobile App, RIAM module changes doesn't reflect in Mobile APP | PCSW |  |  | In Progress | jkulkapv | SQA | Continuation |  |  |  | 2021-10-28 17:24
FDNAT3ADDR-520 | Loop overload related Observations | PO |  |  | Analysis | jdatiru | SQA | Documentation |  |  |  | 2021-10-28 17:06
FDNAT3ADDR-507 | Internal issue Release 01.01.01: Firmware update warning message shows $ | PCSW |  |  | To Do | jgosavj | R&D PC Software | Continuation |  |  |  | 2021-10-19 15:43
FDNAT3ADDR-503 | Out Of Range address trouble generated after Enrolling | Main Panel Code |  |  | To Do | jkulkapv | SQA | Continuation |  |  |  | 2021-10-11 14:26
FDNAT3ADDR-502 | Panel keys stop working when an event is generated after the wrong password entry exceeded the message. | Main Panel Code |  |  | Blocked | jdatiru | SQA | Monitor |  |  |  | 2021-10-11 12:26
FDNAT3ADDR-473 | In the view log menu, some corruption is observed intermittently. | Main Panel Code |  |  | Blocked | jkohilc | SQA | Monitor |  |  |  | 2021-09-15 16:10
FDNAT3ADDR-472 | Though the panel was in normal condition, Test signal 608 was sent to the central station instead of 602. | Gateway |  |  | To Do | jdatiru | SQA | Monitor |  |  |  | 2021-09-14 17:44
FDNAT3ADDR-468 | The panel display window went blank | Main Panel Code |  |  | To Do | jliam | SQA | PdM_Agreement |  |  |  | 2021-09-08 20:51
FDNAT3ADDR-467 | AUX controller and Main overcurrent trouble occurred when NAC overcurrent trouble is created. | Main Panel Code |  |  | Blocked | jkulkapv | SQA | Monitor |  |  |  | 2021-09-08 13:03
FDNAT3ADDR-461 | Not polled trouble generated for few devices, when loop connector removed and connected back after some time. | Main Panel Code |  |  | To Do | jkohilc | SQA | Continuation |  |  |  | 2021-09-02 16:43
FDNAT3ADDR-460 | Config/Job File created from Mobile APP is not compatible/supporting in Panel | MobileApp |  |  | To Do | jshar5 | Product Support | Continuation |  |  |  | 2021-09-01 12:57
FDNAT3ADDR-459 | Internal Defect ¦ After Silence Key SNM is generating NO Answer trouble | Main Panel Code |  |  | To Do | jingola | R&D Firmware | Not_Critical |  |  |  | 2021-08-27 06:45
FDNAT3ADDR-458 | Internal Defect ¦ After 4000 logs overflow, Trouble window is getting corrupted. | Main Panel Code |  |  | To Do | jingola | R&D Firmware | Pd_Limitation |  |  |  | 2021-08-27 06:39
FDNAT3ADDR-445 | Sounder base changes are not reflected in the panel when the Console JSON file is loaded to the panel. | MobileApp | PCSW | PO | In Progress | jkohilc | SQA | Continuation | Pd_Limitation |  |  | 2021-08-24 19:09
FDNAT3ADDR-429 | Though there is no primary path trouble, the gateway transmits all events to the central station from the secondary path instead of the primary path. | Gateway |  |  | To Do | jdatiru | SQA | Continuation |  |  |  | 2021-08-16 14:57
FDNAT3ADDR-420 | When exported JSON file from console to the mobile app, sounder base and assigned zone-related changes did not reflect in the mobile app. | MobileApp | PCSW |  | In Progress | jkohilc | SQA | Continuation | Pd_Limitation |  |  | 2021-08-13 19:39
FDNAT3ADDR-419 | Verify setup related observations | PCSW |  |  | To Do | jkulkapv | SQA | Continuation |  |  |  | 2021-08-13 16:47
FDNAT3ADDR-414 | Gateway configuration option should be possible through installer access instead of user access | Gateway | Main Panel Code |  | To Do | jdatiru | SQA | Documentation |  |  |  | 2021-08-10 15:46
FDNAT3ADDR-411 | Multiple issues found in Console Logs | PCSW |  |  | To Do | jkulkapv | SQA | Continuation |  |  |  | 2021-08-09 19:06
FDNAT3ADDR-410 | Not polled trouble for 51 devices Observed after LAMP Test completed | Main Panel Code |  |  | Blocked | jkulkapv | SQA | Monitor |  |  |  | 2021-08-09 11:57
FDNAT3ADDR-409 | Mobile app is giving error while importing the JSON file, generated from both PCSW and the panel | MobileApp | PCSW |  | In Progress | jkohilc | SQA | Continuation | REOPEN |  |  | 2021-08-06 18:51
FDNAT3ADDR-407 | Gateway is re-configuring intermittently, though no changes are done related to gateway configuration. | Gateway |  |  | In Progress | jdatiru | SQA | Continuation | PdM_Agreement |  |  | 2021-08-05 15:37
FDNAT3ADDR-403 | Internal Issue 01.00.14: JSON export from Console and importing to Mobile app not working forSignal IAM module | PCSW |  |  | To Do | jgosavj | R&D PC Software | Continuation |  |  |  | 2021-07-29 19:51
FDNAT3ADDR-398 | Console gives "USB- PORT ALREADY IN USE" Error pop up when we try to open New installation File while the other file is in use. | PCSW |  |  | To Do | jkulkapv | SQA |  |  |  |  | 2021-07-23 15:05
FDNAT3ADDR-386 | Internal Issue Simplex Mobile Appv0.2.4: Exported Json file from Console is not getting imported into mobile app | MobileApp | PCSW |  | In Progress | jgosavj | Product Support | Continuation | REOPEN |  |  | 2021-07-09 18:54
FDNAT3ADDR-384 | Internal Issue 01.00.12: Configuration report throwing exception for function key | PCSW |  |  | To Do | jgosavj | R&D PC Software | Continuation |  |  |  | 2021-07-09 17:05
FDNAT3ADDR-383 | Internal defect ¦ Start up sequence after multiple power cycles | Main Panel Code |  |  | Blocked | jbiradc | R&D Firmware | Monitor |  |  |  | 2021-07-09 15:12
FDNAT3ADDR-379 | Firmware main controller trouble observed and panel database got erased after a power cycle. | Main Panel Code |  |  | Blocked | jdatiru | SQA | Monitor |  |  |  | 2021-07-07 19:44
FDNAT3ADDR-374 | Internal issue 01.00.12: Application should support at least 3 versions of FW | PCSW |  |  | In Progress | jgosavj | R&D PC Software | Continuation |  |  |  | 2021-07-06 20:02
FDNAT3ADDR-371 | Not polled trouble for 159 devices observed after GW configuring completed | Main Panel Code |  |  | Blocked | jkulkapv | SQA | Monitor |  |  |  | 2021-07-05 11:44
FDNAT3ADDR-361 | Abnormal Behavior observed when Zone disabled and Pull station is activated from different zone | Main Panel Code |  |  | Blocked | jkulkapv | SQA | Monitor |  |  |  | 2021-06-30 09:49
FDNAT3ADDR-339 | Internal Issue 01.00.12 : JSON Parser ¦ Export value of Device, Base TAG is In-correct | PCSW |  |  | To Do | jpunatj | R&D PC Software | Continuation |  |  |  | 2021-06-11 17:26
FDNAT3ADDR-336 | MKS ID: 1040809: Internal issue 01.00.08: USB driver is showing FireClass name in the installation Wizard | PCSW |  |  | In Progress | jgosavj | R&D PC Software | Continuation |  |  |  | 2021-06-08 11:30
FDNAT3ADDR-333 | The device database got erased after Firmware up-gradation from 01.00.11 to 01.00.12. (.bin file via PC Console) | Main Panel Code |  |  | Blocked | jdatiru | SQA | Monitor |  |  |  | 2021-06-04 17:28
FDNAT3ADDR-327 | Firmware main controller trouble observed during testing. | Main Panel Code |  |  | Blocked | jdatiru | SQA | Monitor |  |  |  | 2021-05-28 18:19
FDNAT3ADDR-315 | MKS ID: 996611:SW_Defect_01_00_02: Response from Panel time out error popup while sending device configuration to panel. Â |  |  |  | In Progress | jdatiru | SQA | Continuation | PdM_Agreement |  |  | 2021-05-24 16:28
FDNAT3ADDR-312 | Internal Defect ¦ Mistake Proofing for 'Switching 1' trouble along with Not polled trouble was observed when wrong entry trouble condition was created. | Main Panel Code |  |  | Blocked | jpunatj | R&D Firmware | Monitor |  |  |  | 2021-05-18 19:43
FDNAT3ADDR-299 | Internal Defect ¦ During Start UP Panel doesn't ask for User Password and get gets stuck in Initializing Phase | Main Panel Code |  |  | Blocked | jsubral | R&D Firmware | Monitor |  |  |  | 2021-05-06 11:13
FDNAT3ADDR-297 | Switching 1' trouble along with Not polled trouble was observed when wrong entry trouble condition was created. | Main Panel Code |  |  | Blocked | jkohilc | SQA | Monitor |  |  |  | 2021-05-04 20:07
FDNAT3ADDR-292 | Corrupted/Mismatch Event Screen observed when function keys configuration send from console and executed on Panel | Main Panel Code |  |  | Blocked | jkulkapv | SQA | Monitor |  |  |  | 2021-05-03 14:40
FDNAT3ADDR-270 | MKS ID: 1042539: UL_Critical_FW_Defect_FW_Version_ 01_00_08 A: After performing default data, panel gets stuck in Gateway configuration | PCSW |  |  | Blocked | jkohilc | SQA | Monitor |  |  |  | 2021-04-22 19:35
FDNAT3ADDR-269 | MKS ID: 1042489: UL_Critical_SW_Defect_FW Version_01.00.08: New added mapping type not displayed in event mapping list. | PCSW |  |  | Blocked | jdatiru | SQA | Monitor |  |  |  | 2021-04-22 19:32
FDNAT3ADDR-267 | MKS ID: 1040376: SW_Defect_SW Version_01.00.07: Access violation error displayed during console skin change and application closed. | PCSW |  |  | To Do | jdatiru | SQA | Monitor |  |  |  | 2021-04-22 19:26
FDNAT3ADDR-261 | Help file loading in the panel functionality not working as expected. | Main Panel Code |  |  | Analysis | jkulkapv | SQA | Continuation | PdM_Agreement |  |  | 2021-04-20 19:01
FDNAT3ADDR-259 | MKS ID: 1047726: SW_Defect_SW_version_01.00.09: While global read, FC console gets stuck and displays Â 'Wrong message format' error intermittently. | PCSW |  |  | To Do | jkohilc | SQA | Monitor |  |  |  | 2021-04-19 20:04
FDNAT3ADDR-253 | MKS ID: 1042028: UL_Critical_FW_Defect_FW Version_01.00.08:The PULL STATION does not activate using REED SWITCH | Mechanical |  |  | To Do | jsubral | SQA | Continuation |  |  |  | 2021-04-19 19:46
FDNAT3ADDR-241 | Zone details not displayed in analyze menu for Mini IAM module Event. | Main Panel Code |  |  | Blocked | jdatiru | SQA | Monitor |  |  |  | 2021-04-07 12:35
FDNAT3ADDR-238 | Internal Defect: False Alarm detected by SMK+H+CO detector when 2 km cable is connected. | Main Panel Code |  |  | Blocked | jingola | SQA | Continuation | PdM_Agreement |  |  | 2021-03-29 14:25
FDNAT3ADDR-237 | Cold start AUX trouble generated when USB to USB cable connected from laptop to panel | Hardware | Main Panel Code |  | Analysis | jkulkapv | SQA | Continuation |  |  |  | 2021-03-26 16:47
FDNAT3ADDR-200 | Internal issue 01.00.11: Error Message box appears once click on utilities tab | PCSW |  |  | To Do | jgosavj | R&D PC Software | Continuation |  |  |  | 2021-03-12 18:12
FDNAT3ADDR-182 | Log Event Count Mismatch in PC Console | PCSW |  |  | Blocked | jkulkapv | SQA | Monitor |  |  |  | 2021-02-25 18:32
FDNAT3ADDR-180 | Internal issue 01.00.11: Daylight saving time table not restoring | PCSW |  |  | Analysis | jgosavj | R&D PC Software | Continuation |  |  |  | 2021-02-22 13:13
FDNAT3ADDR-176 | NAC Configuration info is displayed wrong in the mobile app when configured from the PC console | PCSW |  |  | In Progress | jkohilc | SQA | Continuation |  |  |  | 2021-02-19 16:08
FDNAT3ADDR-175 | Incorrect Mode value for Smoke Detector | MobileApp |  |  | In Progress | jpunatj | R&D PC Software | REOPEN |  |  |  | 2021-02-19 13:41
FDNAT3ADDR-174 | Internal Issue 01.00.11 : Incorrect Mode value for Smoke and Smoke Heat Detector | PCSW |  |  | To Do | jpunatj | R&D PC Software | Continuation |  |  |  | 2021-02-19 11:28
FDNAT3ADDR-161 | Â 'Not polled trouble' was generated automatically for all devices after Alarm event. | Main Panel Code |  |  | Blocked | jdatiru | SQA | Monitor |  |  |  | 2021-02-16 13:18
FDNAT3ADDR-148 | Central station Configuration not set as expected in the panel if configured from mobile APP. | Main Panel Code |  |  | In Progress | jdatiru | SQA | Continuation |  |  |  | 2021-02-05 20:02
FDNAT3ADDR-143 | Incorrect password gets configured when panel gets power cycle after default data operation | PO |  |  | In Progress | jdatiru | SQA | Continuation | REOPEN |  |  | 2021-02-05 12:32
FDNAT3ADDR-131 | Isolator is not get activated when the loop terminal is shorted. | Hardware | Main Panel Code |  | Blocked | jdatiru | SQA | Pd_Limitation |  |  |  | 2021-02-02 19:52
FDNAT3ADDR-124 | Device mapping is failing intermittently. | Main Panel Code |  |  | Blocked | jkohilc | SQA | Monitor |  |  |  | 2021-01-31 19:57
FDNAT3ADDR-123 | Multiple issues found related to the panel Help strings. | Main Panel Code |  |  | In Progress | jdatiru | SQA | Not_Critical |  |  |  | 2021-01-29 19:19
FDNAT3ADDR-107 | MKS ID: 988658: FW_Defect_SW_Version_ 1_0_2 : The panel is taking time more than 200 secs to restore the 250 faults | Hardware | Main Panel Code |  | Blocked | jpurkas | SQA | Pd_Limitation |  |  |  | 2021-01-13 12:09
FDNAT3ADDR-103 | MKS ID: 1019340: SW_Defect_SW_Version_ 1_0_5: Access violation error popup displayed during log read. | Main Panel Code |  |  | To Do | jpurkas | SQA | Continuation |  |  |  | 2021-01-13 10:41
FDNAT3ADDR-79 | NAC 1 doesnt activate when other NAC circuit is disabled | Main Panel Code |  |  | Blocked | jsubral | SQA | Monitor |  |  |  | 2021-01-12 00:12
FDNAT3ADDR-76 | Ground fault trouble not detected for Tx terminal of PSTN line. | Gateway | Hardware |  | Blocked | jdatiru | SQA | Pd_Limitation |  |  |  | 2021-01-07 18:25
FDNAT3ADDR-53 | PSTN LINE trouble is not detected when the Transmit cable of the gateway is alone removed and the addition of other trouble creates recurring trouble related to PSTN | Gateway |  |  | Blocked | jsubral | SQA | Pd_Limitation |  |  |  | 2020-12-22 20:47
FDNAT3ADDR-52 | Internal issue 01.00.11: Wrong Programming Page error during global read if Relay 1 is disabled. | PCSW |  |  | To Do | jingola | R&D PC Software | Continuation |  |  |  | 2020-12-22 18:51
FDNAT3ADDR-28 | Internal Defect ¦ When Alarm is present Zone status page is showing Standby in place of Trouble | Main Panel Code |  |  | Blocked | jkhabym | SQA | Continuation |  |  |  | 2020-12-09 20:35
FDNAT3ADDR-13 | Internal Defect ¦ CCB_CCRX ¦ devices getting disabled automatically and NOT POLLED troubles are generated multiple times. | Main Panel Code |  |  | Blocked | jingola | R&D PC Software | Continuation |  |  |  | 2020-11-10 19:00 | Further continuation releases
FDNAT3ADDR-11 | Internal Defect ¦ CCB_CCRX ¦ Loop break gives wrong device count | Main Panel Code |  |  | To Do | jingola | R&D Firmware | Continuation |  |  |  | 2020-11-10 18:31 | Further continuation releases